## CAP Tracker
CAP ID | Finding | Action | Owner | Priority | Due | Status | Closure Evidence
CAP-001 | MFA rollout incomplete | Enable MFA for remaining privileged/risk-sensitive accounts | IT | Critical | 30 days | Open | IAM report showing coverage
CAP-002 | Access review evidence incomplete | Implement quarterly access review and sign-off | IT/Security | High | 45 days | Open | Signed access review
CAP-003 | Security training not formalized | Launch annual awareness program and track completion | HR/IT | High | 60 days | Open | Training completion report
CAP-004 | Vulnerability SLA informal | Approve severity-based patch/remediation SLA | Security/Engineering | High | 45 days | Open | Approved SLA
CAP-005 | Logging retention undefined | Document log retention requirements | Security | High | 45 days | Open | Logging standard
CAP-006 | IR exercise not evidenced | Run tabletop exercise and record lessons learned | Security | Medium | 60 days | Open | Exercise report
CAP-007 | SDLC security gates inconsistent | Implement security checklist for production releases | Engineering | High | 60 days | Open | Completed checklist samples